## provide sprint planning in gant
Task | User Story | Sprint | Start Date | Duration (Days) | Dependencies
Design Claim Form UI | US001.1.1 | 1 | Day 1 | 2
Develop Claim Form Structure | US001.1.1 | 1 | Day 1 | 3 | Design Claim Form UI
Implement Field Validation | US001.1.3 | 1 | Day 3 | 2 | Develop Claim Form Structure
Implement Document Upload | US001.1.2 | 2 | Day 6 | 3 | Develop Claim Form Structure
Develop Claim Review Page | US001.1.4 | 2 | Day 6 | 2 | Implement Field Validation, Implement Document Upload
Implement Claim Submission | US001.1.4 | 2 | Day 8 | 1 | Develop Claim Review Page
Design Claim Tracking Dashboard UI | US001.2.1 | 3 | Day 11 | 2 | Implement Claim Submission
Develop Claim List Display | US001.2.1 | 3 | Day 11 | 2 | Design Claim Tracking Dashboard UI
Implement Claim Status Display | US001.2.2 | 3 | Day 13 | 2 | Develop Claim List Display
Implement Claim Date Display | US001.2.3 | 3 | Day 13 | 1 | Develop Claim List Display
Implement Last Updated Date Display | US001.2.3 | 3 | Day 14 | 1 | Implement Claim Status Display
Sprint 1 Goal:
Basic Claim Submission Form
Sprint 2 Goal:
Claim Submission with Review and Upload
Sprint 3 Goal:
Claim Tracking Dashboard